## Sheet1
|  |  | L | M | H
100
|  | 90 | [6 empty] | H
|  | 80 | [6 empty] | M
|  | 70 | [6 empty] | L
60
50
40
30
20
10
Number | Risk Name | Full Risk Cost | Risk Probability | Factored Risk cost | Risk Impact to Project | Risk Mitigation Plan | Point of Contact | Expected Risk Retire date
1 | Stakeholder milestone payments fail | 20000 | 30% | 6000 | M | focus on deign planning, document procces, and prototyping | PM | First delivery Date
2 | Manufacturing Risk (Increase of product order) | 66000 | 10% | 6600 | H | Plan to hold back 15% of awaard contract amount to afford extra resources if needed | Manufacturing team | 3 months Before Final Delivery date
3 | Shortage of material resources | 180000 | 10% | 18000 | M | Implements mulitple vendor sources and aviablity, delivery schedules tracking | Production team | 2nd Milestone payment
4 | Project schedule and milestone | 43000 | 20% | 8600 | L | Implements failure mode ananlysis with event trees | HR | Before intial program review
5 | Project execution plan | 500000 | 60% | 300000 | M | ensure kickoff and follow up schedules in project scope | Project Planning | After initial project review
6 | Project performance specifications | 200000 | 60% | 120000 | L | impleemnts variations of protoyps with document ocntrol proccess | PM | 2nd Project Review
7 | Project R&D Design Conflict | 95000 | 90% | 85500 | H | Collaberate weekly scrum meeting for all departments. | R&D | Before 1st Intial project review.
8 | Project justification | 80000 | 40% | 32000 | H | Develop full use-case for product an dschedule User test on project review dates | Design team | Before first delivery date
9 | Radio Module design | 562000 | 80% | 449600 | M | Source contractors who have biuld Mil-spec radios to purchase and rev engineer or associate cost ananlysis plan to see if pre-biult units would be cheaper then biulding in house. | R&D | Before 1st Intial project review.
10 | Freezer pac design | 312000 | 60% | 187200 | L | Source contractors who have biuld Mil-spec refrigerator pouches to purchase and rev engineer or associate cost ananlysis plan to see if pre-biult units would be cheaper then biulding in house. | R&D | Before 1st Intial project review.
10
1
2
3
4
5
6
8
9
7