## Example
WBS |  |  | Title | Description | Start Date | End Date | Total estimated days | Point of Contact (POC)
1 |  |  | Develop Work Breakdown Structure (WBS) | Description of work to be completed / milestone | 2016-01-05 | 2016-01-05 | 1
| 1.1 |  | Review customer statement of work (SOW) | Read and review the statement of work | 2016-01-06 | 2016-01-09 | 3 | Project Manager
|  | 1.1.1 | Identify all project deliverables and milestones | Highlight and identify all project deliverables and milestones associtated with the project | 2016-01-06 | 2016-01-09 | 0 | Project Manager
| 1.2 |  | Forward a copy of the customer statement of work to the project team | Forward a copy of the customer statement of work to all project team members | 2016-01-10 | 2016-01-10 | 1 | Project Manager
|  | 1.2.1 | Begin development of the WBS | Develop the WBS | 2016-01-10 | 2016-01-10 | 1 | Project team
| 1.3 |  | Project team review | Set up a SOW team review with the project team | 2016-01-13 | 2016-01-13 | 1 | Project team
|  | 1.3.1 | Identify all top level work packages | Highlight and identify all top level milestones / deliverables | 2016-01-14 | 2016-01-15 | 1 | S. Johnson
| 1.4 |  | Identify all lower level work packages | identify all work associated with the top level milestones | 2016-01-14 | 2016-01-15 | 1 | M. Jones
|  | 1.4.1 | Project team approval | Set up a project team meeting for WBS review / approval | 2016-01-17 | 2016-01-17 | 1 | Project team

## Proj. Work Breakdown Structure
WBS |  |  | Title | Description | Start Date | End Date | Total estimated days | Point of Contact (POC)
1 |  |  | Develop Work Breakdown Structure (WBS) | Description of work to be completed / milestone | 2016-01-05 | 2016-01-05 | 1
| 1.1 |  | Review customer statement of work (SOW) | Read and review the statement of work | 2016-01-06 | 2016-01-09 | 3 | Project Manager
|  | 1.1.1 | Identify all project deliverables and milestones | Highlight and identify all project deliverables and milestones associtated with the project | 2016-01-06 | 2016-01-09 | 0 | Project Manager
| 1.2 |  | Forward a copy of the customer statement of work to the project team | Forward a copy of the customer statement of work to all project team members | 2016-01-10 | 2016-01-10 | 1 | Project Manager
|  | 1.2.1 | Begin development of the WBS | Develop the WBS | 2016-01-10 | 2016-01-10 | 1 | Project team
| 1.3 |  | Project team review | Set up a SOW team review with the project team | 2016-01-13 | 2016-01-13 | 1 | Project team
|  | 1.3.1 | Identify all top level work packages | Highlight and identify all top level milestones / deliverables | 2016-01-14 | 2016-01-15 | 1 | S.Pritchard
| 1.4 |  | Identify all lower level work packages | identify all work associated with the top level milestones | 2016-01-14 | 2016-01-15 | 1 | S.Pritchard
|  | 1.4.1 | Project team approval | Set up a project team meeting for WBS review / approval | 2016-01-17 | 2016-01-17 | 1 | Project team
2 |  |  | Product Prototype | Prototype development of intial backpack | 2015-01-10 | 2015-01-12 | 1 | Project team
| 2.1 |  | Protype Research | pilimanry research for materials | 2015-01-10 | 2015-01-12 |  | R&D Team
|  | 2.1.1 | material researech (kevlar, etc) | fabricks and backpack materials research | 2015-01-10 | 2015-01-12 | 1 | R&D Team
|  | 2.1.2 | MIL-Spec refrigeration materials and compments | refrigeration compnents research | 2015-01-10 | 2015-01-12 | 1 | R&D Team
|  | 2.1.2 | Mil-Spec radio techniacl design standards | radio design compnent material research | 2015-01-10 | 2015-01-12 | 1 | R&D Team
| 2.2 |  | Protype Backpack design |  | 2015-01-11 | 2015-01-06 |  | R&D Team
|  | 2.2.1 | Design of backpack | build sketch and design of backpack | 2015-01-11 | 2015-01-06 | 8 | Design team
|  | 2.2.1 | build proptype of backpack | build out intial prortype of backpack v1.0 | 2015-01-11 | 2015-01-06 | 6 | Design team
| 2.3 |  | Refirgeration module prototype | protype rifrigerator module | 2015-01-11 | 2015-01-06 | 10 | Engineering team
|  | 2.3.1 | intial compenet design | Design of refrigerator module | 2015-01-11 | 2015-01-06 | 10 | Engineering team
|  | 2.3.2 | intital protype developemnt | Build and test refigerator module | 2015-01-11 | 2015-01-06 |  | Engineering team
| 2.4 |  | Radio module prototype | protype radio module | 2015-01-11 | 2015-01-06 | 15 | Engineering team
|  | 2.4.1 | intial compenet design | Design radio module | 2015-01-11 | 2015-01-06 | 15 | Design team
|  | 2.4.2 | intital protype developemnt | build and test radio module | 2015-01-11 | 2015-01-06 | 2 | Design team
| 2.5 |  | Prototype Assembly | Assmeble all compenets | 2015-01-11 | 2015-01-06 | 2 | Design team
|  | 2.5.1 | assemble protype | assemble all compenets of the intial prototype | 2015-01-11 | 2015-01-06 | 10 | Design team
| 2.6 |  | Submit UT(testing) | Customer testing | 2015-01-11 | 2015-01-06 | 10 | Design team
|  | 2.6.1 | user feeddback | Submit and rate customer test US army | 2015-01-11 | 2015-01-06 | 5 | Design team
|  | 2.6.2 | user changes | changes user wants to product | 2015-01-11 | 2015-01-06 | 14 | Design team
3 |  |  | Product manufacturing |  | 2015-06-01 | 2016-10-01 | 30 | Operations team
| 3.1 |  | Product supply order and recsive | revivables of raw materials | 2015-06-01 | 2016-10-01 | 1 | Operations team
|  | 3.1.1 | supply invintory tracking | tracking of raw materials | 2015-06-01 | 2016-10-01 | 1 | Operations team
| 3.2 |  | raw materail production and tracking | manufacturing line products and amterials usage | 2015-06-01 | 2016-10-01 | 1 | Operations team
|  | 3.2.1 | tracking invintory | tracking and invintory of raw material | 2015-06-01 | 2016-10-01 | 1 | Operations team
| 3.3 |  | finish protuct testing | final product engineering testing | 2015-06-01 | 2016-10-01 | 1 | project manager
4 |  |  | Product packing | Packaging and finilization of the product | 2016-10-01 | 2016-05-01 | 2 | Packaging Team
| 4.1 |  | product labeling | labing and invintory count of product | 2016-10-01 | 2016-05-01 | 2 | Packaging Team
|  | 4.1.1 | skew tracking labeling | digital geo location tracking | 2016-10-01 | 2016-05-01 | 5 | Packaging Team
| 4.2 |  | Product shipping and stock | final stock of delvierable items to ship | 2016-10-01 | 2016-05-01 | 5 | Packaging Team
|  | 4.2.1 | resources mailing & shipping labels | adding shipping labels for distrubution | 2016-10-01 | 2016-05-01 | 8 | Packaging Team
5 |  |  | Delivery of products to US Army | Customer product delivery | 2016-10-01 | 2016-05-01 | 1 | Shipping
| 5.1 |  | Ground Forces | Delivery or product to ground forces | 2016-10-01 | 2016-05-01 | 14 | Shipping
|  | 5.1.1 | distribution tracking | tracking 125 units delved to army ground forces | 2016-10-01 | 2016-05-01 | 14 | Shipping
| 5.2 |  | Special operations | Delivery or product to special forces | 2016-10-01 | 2016-05-01 | 14 | Shipping
|  | 5.2.1 |  | tracking 125 units delved to army special forces | 2016-10-01 | 2016-05-01 | 14 | Shipping
5.3
5.3.1
5.4
5.4.1
6
6.1
6.2.1
6.2
6.2.1
6.3
6.3.1
6.4
6.4.1
7
7.1
7.1.1
7.2
7.2.1
7.3
7.3.1
7.4
7.4.1
8
8.1
8.1.1
8.2
8.2.1
8.3
8.3.1
8.4
8.4.1
9
9.1
9.1.1
9.2
9.2.1
9.3
9.3.1
9.4
9.4.1
10
10.1
10.1.1
10.2
10.2.1
10.3
10.3.1
10.4
2.4.1